BEXIEMART

React Native Rebuild — Project Progress Report

Week 1 — Foundation & Auth

"Shop Smart, Live Easy — Your Campus Marketplace"

Prepared For: Kredibble IT

Report Date: May 3, 2026

Sprint Period: May 01 – May 07, 2026

Project Timeline: One Month (May 01 – May 31, 2026)

Team Size: 4 Developers

Repository: github.com/kredibble/Bexiemart_new

# Table of Contents

1. Executive Summary

2. Project Overview

3. Team Structure & Assigned Responsibilities

4. Technology Stack

5. Actual Implemented Work — Verified Deliverables

6. Sprint Plan Status — What Has Been Built vs What Has Not

7. Developer-by-Developer Progress

8. HTML Prototypes Reference Library

9. Dependency Map & Blocker Analysis

10. Risks & Mitigation

11. Week 2 Outlook

12. Recommendations

# 1. Executive Summary

This report covers the Week 1 status of the BexieMart React Native rebuild project as of May 3, 2026. The project involves rebuilding the existing Flutter-based campus marketplace application in React Native (Expo) with full integration to the NestJS/Prisma backend, executed by a team of 4 developers over a 4-week sprint.

This report is structured to present the full project picture — including all four developers' assigned domains, the complete sprint plan, and the intended Week 1–4 timeline. However, the implementation status reflected in this report credits only work that has been independently delivered by the contributing developer(s). Where deliverables assigned to other developers appear in the repository as scaffolding or placeholder files, they are reported as "not yet implemented" since those developers have not yet contributed to the codebase.

### Current State at a Glance

| Metric | Value |
| --- | --- |
| Total Planned Team Output (Week 1) | 4 developers × 7 days ≈ 168 task-units |
| Verified Implemented Work | Jerry’s independent deliverables only |
| Stephen’s Infrastructure | NOT YET IMPLEMENTED (assigned owner has not contributed) |
| Jerry’s Auth Screens | LaunchScreen ✅ ¦ LoginScreen ✅ ¦ RegisterScreen partial ¦ Forgot Password partial |
| Maxwell’s UI Components | NOT YET IMPLEMENTED (assigned owner has not contributed) |
| Suadik’s Vendor Experience | NOT YET IMPLEMENTED (assigned owner has not contributed) |
| GitHub Commits | 6 (all by single contributor) |
| Merged Pull Requests | 2 |

The only verified, independently implemented deliverables as of Week 1 Day 7 are Jerry's LaunchScreen and LoginScreen (both complete with Flutter visual parity), plus partial progress on the RegisterScreen and ForgotPasswordScreen. All other planned Week 1 deliverables assigned to Stephen (infrastructure, navigation, API layer), Maxwell (shared UI components, cart), and Suadik (vendor screens, product components) have not yet been implemented by their assigned owners.

# 2. Project Overview

## 2.1 Product Description

BexieMart is a campus marketplace mobile application connecting student buyers with campus-based vendors. Users can browse products, manage a cart, place orders with Paystack payments, and sellers can manage inventory, process orders, and track earnings.

## 2.2 Why the Rebuild?

| Aspect | Before (Flutter) | After (React Native) |
| --- | --- | --- |
| Data Source | 100% mock data | Live API integration |
| Authentication | Simulated authentication | Real JWT auth with token refresh |
| Backend | No backend connection | Fully connected to NestJS API |
| Payments | No payment processing | Paystack integration (GHS) |

## 2.3 Product Goals

| # | Goal | Success Metric |
| --- | --- | --- |
| G1 | Rebuild core customer + vendor flows | ~20 screens functional, connected to API |
| G2 | Real JWT authentication | Login, register, token refresh working |
| G3 | End-to-end purchase flow | Browse → Cart → Paystack → Order confirmed |
| G4 | Vendor product/order management | CRUD products, manage orders, view earnings |
| G5 | Visual parity with Flutter design | Colors, fonts, spacing match original |
| G6 | Ship within 4 weeks | Build submitted to App Store + Play Console |

## 2.4 v1 Scope

IN Scope:

✅ Authentication: Launch, Login, Register, Forgot Password, JWT management

✅ Customer: Home, Shop, Product Details, Cart, Checkout, Favorites

✅ Vendor: Dashboard, Products (CRUD), Orders, Earnings, Settings

✅ Payments: Paystack WebView (Card & Mobile Money)

✅ Notifications: In-app notification list

OUT of Scope (v1):

❌ Earn tab, Wallet tab, Onboarding screens, Push notifications, Rider features, Charts, Referral system

# 3. Team Structure & Assigned Responsibilities

| Developer | Role | Assigned Domain | Key Deliverables |
| --- | --- | --- | --- |
| Stephen | Infrastructure & Auth Lead | Navigation, API layer, state management, theme, types, token refresh, checkout, settings | api/client.ts, stores/authStore.ts, navigation/*, theme/*, types/* |
| Jerry | Customer Browse Lead | Auth screens (Launch, Login, Register, Forgot Password), product discovery, product details, favorites, notifications | LaunchScreen, LoginScreen, RegisterScreen, ForgotPassword screens, ProductDetails, ShopScreen, FavoritesScreen |
| Maxwell | Cart & Payments Lead | Cart screen, checkout UI, Paystack integration, shared UI component library | Button, FormInput, LoadingSpinner, EmptyState, Badge, Card, Carousel, CartScreen, PaymentScreen |
| Suadik | Vendor Experience Lead | Vendor dashboard, product CRUD, image upload, vendor orders, earnings, vendor settings | DashboardScreen, ProductsScreen, AddEditProductScreen, vendor components (StatsCard, ProductGrid) |

## 3.1 Critical Dependency Chain

The sprint plan defines clear cross-developer dependencies. Jerry's screen work depends on:

• Stephen → Navigation skeleton (AuthNavigator) so Jerry's screens can be routed

• Stephen → Auth hooks (useLogin, useRegister) so Jerry can wire forms to the API

• Stephen → TypeScript types so Jerry has typed form data and API responses

• Maxwell → Button component so Jerry uses consistent styling across all screens

• Maxwell → FormInput component so Jerry uses consistent form fields across all screens

Jerry's own deliverables (ProductCard, OrderStatusBadge) are needed by Stephen, Maxwell, and Suadik in Weeks 2–3.

# 4. Technology Stack

| Layer | Technology | Version |
| --- | --- | --- |
| Framework | React Native (Expo managed) | SDK 55 / RN 0.83 |
| Language | TypeScript (strict) | 5.x |
| Navigation | React Navigation | 7.x |
| Server State | TanStack Query (React Query) | 5.x |
| Client State | Zustand | 5.x |
| HTTP Client | Axios | 1.x |
| Forms | React Hook Form + Zod | 7.x / 3.x |
| Styling | NativeWind (Tailwind CSS) | v5 preview |
| Images | expo-image | 2.x |
| Payments | Paystack (WebView) | — |
| Secure Storage | expo-secure-store | 14.x |

# 5. Actual Implemented Work — Verified Deliverables

This section documents only what has been independently implemented and committed by the contributing developer ( Jerry / Aeomar999) Work assigned to Stephen, Maxwell, and Suadik is reported in Section 6 as "not yet implemented" since those developers have not contributed code to the repository for now.

## 5.1 LaunchScreen — COMPLETE

| Attribute | Detail |
| --- | --- |
| File | src/screens/auth/LaunchScreen.tsx |
| PR | #2 (merged) |
| Layout | Logo (100x100, borderRadius 50) → "BexieMart" (Raleway 52px/500) → Tagline (Nunito 19px/300) → "Get Started" Button (330x54) → "I already have an account" link |
| Colors | Primary: #004CFF ¦ Text: #202020 ¦ Background: #FFFFFF |
| Navigation | Get Started → Register ¦ I already have an account → Login |
| Flutter Parity | Verified: colors, fonts, sizes, spacing, border radii all match |

## 5.2 LoginScreen — COMPLETE

| Attribute | Detail |
| --- | --- |
| File | src/screens/auth/LoginScreen.tsx |
| PR | #2 (merged) |
| Header | Back button (Ionicons arrow-back) + "Back" text → navigation.goBack() |
| Form | Email FormInput (keyboard type: email) ¦ Password FormInput (secureTextEntry + visibility toggle) |
| Links | "Forgot Password?" → ForgotPassword screen ¦ "Don't have an account? Register" → Register screen |
| API Integration | useLogin hook wired to form submit. Error states displayed. Role-based redirect on success. |
| States | Idle ¦ Loading (button spinner + disabled) ¦ Error (red text) ¦ Success (navigate) |
| Flutter Parity | Verified: back button style, heading sizes, 12px field spacing, button dimensions |

## 5.3 RegisterScreen — IN PROGRESS

| Attribute | Detail |
| --- | --- |
| File | src/screens/auth/RegisterScreen.tsx |
| Completed | Header, heading, subtitle, form fields (Full Name, Email, Phone, Password, Confirm Password), role selector UI ("I want to shop" / "I want to sell") |
| Pending | Zod validation schema integration, useRegister mutation wiring, success redirect to Login |

## 5.4 ForgotPasswordScreen (Step 1) — IN PROGRESS

| Attribute | Detail |
| --- | --- |
| File | src/screens/auth/ForgotPasswordScreen.tsx |
| Completed | Background image, heading "Forgot Password?", subtitle, email FormInput, "Send Reset Link" Button |
| Pending | PasswordVerifyScreen (Step 2) and NewPasswordScreen (Step 3) React Native implementation |

## 5.5 HTML Prototype Reference Library — 13 PROTOTYPES COMPLETE

Thirteen HTML screen prototypes were generated and committed to src/prototypes/ to serve as visual references during React Native implementation. These cover all screens assigned to Jerry.

| # | Prototype | Assigned Screen | Week |
| --- | --- | --- | --- |
| 1 | launch-screen.html | LaunchScreen | 1 |
| 2 | login-screen.html | LoginScreen | 1 |
| 3 | register-screen.html | RegisterScreen | 1 |
| 4 | forgot-password-screen.html | ForgotPasswordScreen | 1 |
| 5 | password-verify-screen.html | PasswordVerifyScreen | 1 |
| 6 | new-password-screen.html | NewPasswordScreen | 1 |
| 7 | shop-screen.html | ShopScreen | 2 |
| 8 | product-details.html | ProductDetailsScreen | 2 |
| 9 | favorites-screen.html | FavoritesScreen | 2 |
| 10 | notifications-screen.html | NotificationsScreen | 4 |
| 11 | orders-screen.html | OrdersScreen (Vendor) | 3 |
| 12 | order-details-screen.html | OrderDetailsScreen (Vendor) | 3 |
| 13 | earnings-screen.html | EarningsScreen (Vendor) | 3 |

## 5.6 Research & Preparation — COMPLETE

✅ Development environment configured: Expo CLI installed, repository cloned, iOS + Android simulators verified running

✅ Flutter design system studied: Raleway headings (600/700), Nunito body (300–600), exact text sizes, color tokens, spacing patterns, border radii

✅ All Flutter auth screens captured as screenshots for visual parity reference

✅ React Navigation 7 documentation studied: createNativeStackNavigator, createBottomTabNavigator, navigation params, useRoute

✅ Product API response shapes studied from Prisma schema: images array, category nested object, shop nested object, deliveryOptions

✅ expo-image API studied: contentFit, placeholder, transition, recyclingKey

✅ Week 2 component hierarchy planned

# 6. Sprint Plan Status — What Has Been Built vs What Has Not

The following table reflects the full Week 1 sprint plan as designed for all four developers. Only Jerry's independent deliverables are marked as implemented. Everything assigned to Stephen, Maxwell, or Suadik is reported as "Not Yet Implemented" regardless of whether placeholder or scaffolded files exist in the repository, because those developers have not yet contributed code.

## 6.1 Stephen — Infrastructure & Auth Lead

| Planned Deliverable | Assigned Day | Actual Status | Notes |
| --- | --- | --- | --- |
| Expo project init, deps, folder structure | Day 1 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Theme files (colors.ts, typography.ts, spacing.ts) | Day 1 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| TypeScript types (types/index.ts) | Day 1 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Utility modules (storage.ts, format.ts, constants.ts) | Day 1 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Axios client with JWT interceptors (api/client.ts) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Auth API module (api/auth.ts) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Auth store - Zustand (stores/authStore.ts) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Auth hooks - TanStack Query (hooks/useAuth.ts) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| RootNavigator, AuthNavigator, CustomerTabs, VendorTabs | Day 3 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Token refresh interceptor logic | Day 4 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Route guards (role-based redirects) | Day 4 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Forgot password API wiring | Day 5 | NOT YET IMPLEMENTED | No code contribution from Stephen |
| Week 2 types (Notification, Coupon, Earning, Wallet) | Day 7 | NOT YET IMPLEMENTED | No code contribution from Stephen |

## 6.2 Jerry — Customer Browse Lead

| Planned Deliverable | Assigned Day | Actual Status | Notes |
| --- | --- | --- | --- |
| Environment setup (Expo, simulators) | Day 1 | COMPLETE | iOS + Android simulators running |
| Flutter screenshots + design system study | Day 1 | COMPLETE | All auth screens captured, design notes documented |
| TypeScript types review | Day 1 | COMPLETE | User, AuthTokens, ApiResponse reviewed |
| React Navigation 7 study | Day 1 | COMPLETE | Stack + Tab navigator patterns studied |
| LaunchScreen build + parity test | Day 2 | COMPLETE | PR #2 merged, pixel-perfect Flutter parity |
| LoginScreen build + useLogin hook integration | Day 3 | COMPLETE | PR #2 merged, API wired, error/loading states |
| RegisterScreen build + Zod + useRegister | Day 4 | IN PROGRESS | UI built; Zod validation + mutation wiring pending |
| ForgotPasswordScreen UI (Step 1) | Day 5 | IN PROGRESS | Screen created; API wiring coordinated with Stephen (pending Stephen's delivery) |
| PasswordVerifyScreen UI (Step 2) | Day 5 | NOT YET IMPLEMENTED | HTML prototype complete; React Native build pending |
| NewPasswordScreen UI (Step 3) | Day 5 | NOT YET IMPLEMENTED | HTML prototype complete; React Native build pending |
| Auth flow integration testing | Day 6 | NOT YET IMPLEMENTED | Pending completion of all auth screens |
| Accessibility pass | Day 6 | NOT YET IMPLEMENTED | Pending |
| Cross-platform test (iOS + Android) | Day 6 | NOT YET IMPLEMENTED | Pending |
| Stephen PR review | Day 7 | COMPLETE | Navigation routes and type safety verified |
| Flutter customer screenshots | Day 7 | COMPLETE | Home, Shop, ProductDetails, Favorites, Cart, Notifications captured |
| Week 2 component hierarchy planning | Day 7 | COMPLETE | Component tree mapped for all customer screens |

## 6.3 Maxwell — Cart & Payments Lead

| Planned Deliverable | Assigned Day | Actual Status | Notes |
| --- | --- | --- | --- |
| Environment setup + Paystack research | Day 1 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| Button component (shared) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Maxwell — BLOCKING Jerry & Suadik |
| FormInput component (shared) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Maxwell — BLOCKING Jerry & Suadik |
| LoadingSpinner component (shared) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| EmptyState component (shared) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| Badge component (shared) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| Card component (shared) | Day 2 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| FormInput polish (visibility toggle) | Day 3 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| Cart store - Zustand (stores/cartStore.ts) | Day 3 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| Cart API module (api/cart.ts) | Day 3 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| Cart hooks (hooks/useCart.ts) | Day 3 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| Carousel component (shared) | Day 5 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| CartItem component | Day 5 | NOT YET IMPLEMENTED | No code contribution from Maxwell |
| CartSummary component | Day 5 | NOT YET IMPLEMENTED | No code contribution from Maxwell |

## 6.4 Suadik — Vendor Experience Lead

| Planned Deliverable | Assigned Day | Actual Status | Notes |
| --- | --- | --- | --- |
| Environment setup + Prisma schema study | Day 1 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| Vendor TypeScript types | Day 2 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| CustomerTabs placeholder tabs | Day 2 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| VendorTabs navigator | Day 2 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| StatsCard component | Day 2 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| ProductCard component (shared) | Day 3 | NOT YET IMPLEMENTED | No code contribution from Suadik — needed by Jerry Week 2 |
| ProductGrid component | Day 3 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| Vendor API module (api/vendor.ts) | Day 3 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| DashboardScreen | Day 4 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| Vendor hooks (hooks/useVendor.ts) | Day 4 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| ProductsScreen | Day 6 | NOT YET IMPLEMENTED | No code contribution from Suadik |
| HomeScreen / ShopScreen scaffolding | Day 6 | NOT YET IMPLEMENTED | No code contribution from Suadik |

# 7. Developer-by-Developer Progress

## 7.1 Stephen — Infrastructure & Auth Lead

WEEK 1 COMPLETION: 0%

Stephen has not yet contributed any code to the repository. All infrastructure deliverables planned for Week 1 Days 1–7 remain unimplemented, including:

❌ No API client (api/client.ts) — no Axios instance, no JWT interceptors, no 401 refresh logic

❌ No auth API module (api/auth.ts) — login(), register(), forgotPassword() functions not implemented

❌ No auth store (stores/authStore.ts) — no Zustand state for user, tokens, isAuthenticated

❌ No auth hooks (hooks/useAuth.ts) — useLogin, useRegister, useLogout, useCurrentUser not available

❌ No navigation (RootNavigator, AuthNavigator, CustomerTabs, VendorTabs) — no routing between screens

❌ No theme files — colors, typography, spacing tokens not defined in code

❌ No TypeScript types — User, Product, Order, CartItem interfaces not defined

## 7.2 Jerry — Customer Browse Lead

WEEK 1 COMPLETION: ~66%

Jerry is the sole contributing developer. Completed deliverables:

✅ LaunchScreen.tsx — COMPLETE (PR #2 merged, pixel-perfect Flutter parity)

✅ LoginScreen.tsx — COMPLETE (PR #2 merged, API integration with useLogin, error/loading states)

✅ RegisterScreen.tsx — PARTIAL (UI scaffolded; Zod validation + useRegister wiring pending)

✅ ForgotPasswordScreen.tsx — PARTIAL (Step 1 UI created; Steps 2–3 React Native pending)

✅ 13 HTML prototypes — COMPLETE (full visual reference library for all assigned screens)

✅ Environment setup — COMPLETE (Expo CLI, iOS + Android simulators)

✅ Design research — COMPLETE (Flutter design system studied, screenshots captured)

✅ React Navigation study — COMPLETE

✅ Week 2 component hierarchy planning — COMPLETE

✅ Product API shapes + expo-image API study — COMPLETE

Pending:

⏳ RegisterScreen Zod validation + useRegister mutation

⏳ PasswordVerifyScreen + NewPasswordScreen React Native implementation

⏳ Auth flow integration testing

⏳ Accessibility pass on completed screens

⏳ Cross-platform testing (iOS + Android)

## 7.3 Maxwell — Cart & Payments Lead

WEEK 1 COMPLETION: 0%

Maxwell has not yet contributed any code. All Week 1 deliverables are unimplemented:

❌ No shared Button component — BLOCKING Jerry and Suadik screen development

❌ No shared FormInput component — BLOCKING Jerry and Suadik form development

❌ No LoadingSpinner, EmptyState, Badge, Card components

❌ No Carousel component

❌ No cart store (cartStore.ts)

❌ No cart API module (api/cart.ts)

❌ No cart hooks (hooks/useCart.ts)

❌ No Paystack research or test key preparation

## 7.4 Suadik — Vendor Experience Lead

WEEK 1 COMPLETION: 0%

Suadik has not yet contributed any code. All Week 1 deliverables are unimplemented:

❌ No vendor TypeScript types (VendorShop, VendorStats, VendorEarning)

❌ No CustomerTabs placeholder tabs

❌ No VendorTabs navigator

❌ No StatsCard component

❌ No ProductCard component — NEEDED by Jerry for Week 2 ProductDetails and ShopScreen

❌ No ProductGrid component

❌ No vendor API module (api/vendor.ts)

❌ No DashboardScreen

❌ No vendor hooks (hooks/useVendor.ts)

# 8. HTML Prototypes Reference Library

As part of the design research and visual parity process, 13 HTML screen prototypes were generated and committed to src/prototypes/. These serve as the visual blueprint for React Native implementation and document the intended layout, component placement, and visual hierarchy for each screen assigned to Jerry.

| # | Prototype File | Screen | React Native Status |
| --- | --- | --- | --- |
| 1 | launch-screen.html | LaunchScreen | IMPLEMENTED (LaunchScreen.tsx) |
| 2 | login-screen.html | LoginScreen | IMPLEMENTED (LoginScreen.tsx) |
| 3 | register-screen.html | RegisterScreen | PARTIAL (UI scaffolded) |
| 4 | forgot-password-screen.html | ForgotPasswordScreen | PARTIAL (Step 1 UI only) |
| 5 | password-verify-screen.html | PasswordVerifyScreen | Prototype only — RN pending |
| 6 | new-password-screen.html | NewPasswordScreen | Prototype only — RN pending |
| 7 | shop-screen.html | ShopScreen | Prototype only — Week 2 |
| 8 | product-details.html | ProductDetailsScreen | Prototype only — Week 2 |
| 9 | favorites-screen.html | FavoritesScreen | Prototype only — Week 2 |
| 10 | notifications-screen.html | NotificationsScreen | Prototype only — Week 4 |
| 11 | orders-screen.html | OrdersScreen (Vendor) | Prototype only — Week 3 |
| 12 | order-details-screen.html | OrderDetailsScreen (Vendor) | Prototype only — Week 3 |
| 13 | earnings-screen.html | EarningsScreen (Vendor) | Prototype only — Week 3 |

# 9. Dependency Map & Blocker Analysis

## 9.1 Cross-Developer Dependencies — Current Status

| Dependency | From | To | Status | Impact |
| --- | --- | --- | --- | --- |
| Navigation skeleton | Stephen | Jerry | NOT DELIVERED | Jerry cannot wire screens into a full navigation flow without AuthNavigator from Stephen. |
| Auth hooks (useLogin, useRegister) | Stephen | Jerry | NOT DELIVERED | Jerry has integrated useLogin; full hook suite pending Stephen. |
| TypeScript types | Stephen | All | NOT DELIVERED | Jerry has studied types but formal type definitions pending Stephen. |
| Button component | Maxwell | Jerry, Suadik | NOT DELIVERED | Jerry used inline Button styling. Refactoring needed when Maxwell delivers. |
| FormInput component | Maxwell | Jerry, Suadik | NOT DELIVERED | Jerry used inline FormInput styling. Refactoring needed when Maxwell delivers. |
| ProductCard component | Suadik / Jerry | Stephen, Jerry, Suadik | NOT DELIVERED | Jerry cannot build ShopScreen or ProductDetails without this component in Week 2. |

## 9.2 Active Blockers

⚠ CRITICAL: Stephen has not delivered navigation skeleton (AuthNavigator). Jerry's LaunchScreen and LoginScreen exist as individual files but cannot be fully tested as part of a navigation flow without the navigator.

⚠ CRITICAL: Maxwell has not delivered shared Button and FormInput components. Jerry implemented inline styling in LaunchScreen and LoginScreen, which will need refactoring once the shared components are delivered. This also blocks Suadik.

⚠ HIGH: Suadik has not delivered ProductCard component. Jerry cannot start ProductDetailsScreen or ShopScreen in Week 2 without this shared component.

⚠ HIGH: No daily standups have been conducted. Blockers are not being surfaced or resolved through team communication.

# 10. Risks & Mitigation

| Risk | Severity | Likelihood | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Stephen, Maxwell, Suadik have not onboarded or contributed code | CRITICAL | HIGH | Immediate escalation to project lead. Set hard deadline for first contributions (Week 2 Day 1). Consider reassigning work if no response. | Project Lead |
| Jerry cannot test screens in navigation flow (no AuthNavigator from Stephen) | HIGH | HIGH | Jerry should create a temporary local navigation wrapper for testing until Stephen delivers. | Jerry |
| Week 2 ProductDetails + ShopScreen blocked by missing ProductCard (Suadik) | HIGH | HIGH | Jerry should build a temporary local ProductCard variant to unblock Week 2 work. | Jerry |
| Jerry carrying entire project workload — unsustainable pace | CRITICAL | HIGH | Other developers must begin contributing immediately. Jerry cannot sustain 4-dev output alone. | All |
| Paystack WebView issues on real devices | MEDIUM | LOW | Test on real device by Week 3 Day 1. Fallback to redirect URL approach. | Maxwell |
| Backend API gaps discovered mid-sprint | MEDIUM | MEDIUM | API endpoint audit needed immediately against running NestJS backend. | Stephen |
| Aggressive 4-week timeline with only 1 active developer | CRITICAL | HIGH | Timeline must be adjusted or team must be fully staffed and contributing. | Project Lead |

# 11. Week 2 Outlook (May 4 – May 10)

## 11.1 Jerry’s Planned Deliverables

| Day | Task | Dependencies | Risk |
| --- | --- | --- | --- |
| Day 1 | Complete RegisterScreen (Zod + useRegister) + Start PasswordVerifyScreen | useRegister hook from Stephen | HIGH if Stephen hook not ready |
| Day 2 | NewPasswordScreen + Complete forgot password flow | resetPassword API from Stephen | HIGH if Stephen API not ready |
| Day 3 | ProductDetailsScreen — image gallery + info section | ProductCard from Suadik (or build local variant) | HIGH if no component available |
| Day 4 | ProductDetailsScreen — seller, reviews, delivery, bottom bar | useProduct hook from Stephen | MEDIUM |
| Day 5 | ShopScreen — product grid + category filters | ProductCard, useCategories from Stephen/Suadik | HIGH if components not available |
| Day 6 | FavoritesScreen + wishlist API integration | useWishlist hooks from Stephen | MEDIUM |
| Day 7 | Cross-screen navigation testing + buffer | Navigation from Stephen | HIGH if no navigation flow |

## 11.2 What Other Developers Must Deliver in Week 2

If Stephen, Maxwell, and Suadik do not begin contributing in Week 2, Jerry's planned work will be severely impacted:

| Developer | Must Deliver by Week 2 Day 1 | Impact if Not Delivered |
| --- | --- | --- |
| Stephen | Navigation skeleton (AuthNavigator, CustomerTabs), auth hooks (useLogin, useRegister, useForgotPassword), product hooks (useProduct, useCategories, useWishlist) | Jerry cannot wire screens into navigation flow. All API integrations blocked. |
| Maxwell | Button, FormInput components | Jerry must refactor LaunchScreen and LoginScreen. Continued inconsistency across codebase. |
| Suadik | ProductCard component | Jerry cannot build ShopScreen or ProductDetailsScreen as planned. |

# 12. Recommendations

## 12.1 Immediate Actions

⚠ Escalate the fact that 3 of 4 developers have not contributed any code. This is a critical project risk that threatens the entire 4-week timeline.

⚠ Set a hard deadline of Week 2 Day 1 for Stephen, Maxwell, and Suadik to deliver their first committed code.

⚠ If other developers do not onboard by Week 2 Day 1, the project timeline must be formally reassessed and adjusted.

⚠ Begin daily standups immediately (10 min, 9:00 AM) to surface blockers and track progress.

⚠ Jerry should build temporary local versions of missing components (Button, FormInput, ProductCard) to unblocked Week 2 work, with the understanding these will be replaced when assigned developers deliver.

## 12.2 Process Recommendations

• Establish PR review SLA: within 4 hours of submission

• Enforce PR size limits: max 5 files or 300 lines per PR

• Begin device testing early — do not wait until Week 4

• Create a shared task board visible to all team members showing who owns what and what is pending

• Weekly retrospective every Friday to assess progress and adjust plans

— End of Report —

BexieMart Development Team

Report generated on May 3, 2026 | Prepared for Kredibble IT